CARE-ASR — Final Execution Plan

Compressed 4-Person Parallel Build — July 20 to July 31, 2026

Verified against the CARE-ASR Feasibility & Execution Report — Sequenced by Risk, Built in Parallel, Zero Assumed Numbers

Team: Ankit (Integration & Coding) · Mahi (Testing & Face) · Aarth (Data Lead, reports to Ankit) · Divya (Preprocessing, reports to Aarth)

──────────────────────────────────────────────────────────────────────

0. Read This First — Full Task List, All 4 People, Before Anything Else

Every task below is drawn directly from the verified Feasibility & Execution Report's 4-person/2-3-week compressed addendum, mapped onto your actual names and reporting chain. Nothing here is invented — where the source used generic roles (Person A/B/C/D), this plan maps them 1:1 onto your team based on the split you specified.

0.1 Role Mapping — Source Report vs. Your Team

| Source Report Role | What That Role Owns | Mapped To |
| --- | --- | --- |
| Person C — Infra/Eval Engineer (integration owner, holds the scoreboard, continuous) | Baseline harness, WER/M-WER scoring, daily integration merges, latency benchmarking | Ankit |
| Person A — ML Research Lead (entropy gate, correction LLM) | Tsallis entropy gate, few-shot/QLoRA correction wiring, UNSURE fallback | Ankit + Mahi jointly (max shared work) |
| — (testing, Definition-of-Done unit tests) | Unit tests per module, ablation checkpoint verification, latency measurement checks | Mahi |
| Person B — Retrieval Engineer (FAISS/RRF, Kaggle-heavy) | Semantic + phonetic FAISS indices, RRF fusion, dataset preprocessing | Divya(Leads), Aarth (support) |
| Person D — Domain/Data Writer | NER entity tagging, category thresholds, error analysis, report writing | Aarth (leads), Divya supports where preprocessing overlaps |

0.2 Full Task List — Everyone's Work, At A Glance (Read Before Your Own Section)

| # | Task | Owner | Day(s) | Depends On |
| --- | --- | --- | --- | --- |
| S1 | Interface-first meeting: lock exact function signatures/data schemas for retrieval-candidate object, entropy-gate output, scoreboard input format — written down, not verbal | Whole team | Day 1 | First thing done |
| S2 | Confirm scope cuts locked (Section 3) and everyone's environment/compute access working | Whole team | Day 1 | S1 |
| S3 | Whisper output_scores probe — confirm per-token confidence extraction works on 1 real clip before anything else in the entropy workstream begins | Ankit | Day 1 | S1 |
| T1 | Baseline harness live: Whisper-medium inference + WER/M-WER/per-category Recall scoring on AfriSpeech-200 clinical test split | Ankit | Day 1-2 | S3 |
| T2 | Semantic FAISS index: ClinicalBERT embeddings over RxNorm/UMLS concepts, built and query-tested in isolation | Divya (build), Aarth (validate) | Day 1-3 | S1 |
| T3 | Entropy gate implemented and unit-tested on Whisper decoder outputs from T1's baseline run, in isolation from retrieval | Ankit + Mahi | Day 2-4 | T1, S3 |
| T4 | NER entity tagging pipeline (BioBERT/ClinicalBERT) run over the AfriSpeech clinical test set to produce MED/COND/ANA/TTP/PHI reference spans the scoreboard needs | Aarth (leads), Divya (supports) | Day 2-4 | T1 |
| T5 | First integration checkpoint: stub-wired gate + retrieval pass-through (no LLM yet) + scoreboard — confirms pipeline SHAPE works end-to-end before any component is finished | Whole team | Day 4 | T1, T2, T3, T4 |
| T6 | Phonetic FAISS index: mine REAL drug-name pronunciations directly from AfriSpeech-200 clinical clips (NOT synthetic TTS — this is the corrected, faster approach), extract HuBERT embeddings, RRF-fuse with semantic index | Divya (build), Aarth (validate) | Day 4-6 | T2, T5 |
| T7 | Wire a real correction step: few-shot prompting (Qwen2.5-7B-Instruct primary, Llama-3.1 optional upgrade) against fused retrieval candidates — NO fine-tuning yet, per the locked scope cut | Ankit + Mahi | Day 5-7 | T5 |
| T8 | Category-specific thresholds drafted from Day 1 baseline error patterns (lower threshold for MED, higher for ANA) | Aarth (leads), Divya (supports) | Day 6-7 | T4, T1 |
| T9 | Second integration checkpoint: full pipeline with dual retrieval + few-shot correction, scored on the harness — this is the FIRST real ablation number | Whole team | Day 7 | T6, T7, T8 |
| T10 | UNSURE fallback added: three-way CORRECT/WRONG/UNSURE step in the correction prompt/model; on UNSURE, pass through Whisper's original token unchanged | Ankit + Mahi | Day 8-10 | T9 |
| T11 | Tune category thresholds against Week 1's ablation numbers; run error analysis; start pulling qualitative examples for the report | Aarth (leads), Divya (supports) | Day 8-10 | T9 |
| T12 | Latency pass on the fused retrieval layer: batch FAISS queries, cache embeddings so the gating latency claim holds up under real measurement | Divya (build), Aarth (validate) | Day 8-11 | T6 |
| T13 | OPTIONAL upgrade: QLoRA fine-tune of the correction model on MedQuAD-derived examples — ONLY if Day 7's few-shot numbers justify it and compute is free (see Section 3 scope cuts) | Ankit + Mahi | Day 9-12 (conditional) | T9, capacity check |
| T14 | Run the frozen Week 1 pipeline over EKA + Svarah (pure inference, no retraining) — India context table | Divya (build), Aarth (validate) | Day 9-12 (parallel to T13) | T9 |
| T15 | Third integration checkpoint: full pipeline with UNSURE fallback + tuned thresholds, scored on AfriSpeech-200 + India datasets | Whole team | Day 12 | T10, T11, T12, T14 |
| T16 | Freeze the ablation table: baseline -> naive correction -> dual retrieval -> entropy-gated -> thresholded -> UNSURE. Apply the 2 mandatory numeric corrections (Section 5) | Aarth + Ankit | Day 13 | T15 |
| T17 | Written report/claims draft, error examples, visualizations — in parallel with any remaining fixes | Whole team, Mahi leads demo prep | Day 13-14 | T16 |
| T18 | Final whole-system check against Section 8's checklist + demo rehearsal (Mahi as presenting face) | Whole team | Day 14 (July 31) | T17 |

1. Handoff & Dependency Flowchart

This is the literal shape of the build — two shared integration points only (the scoreboard and the fused-retrieval output), exactly as verified in the source report's parallelization rule. Everything else runs independently and merges via stubs.

1.1 Day 1 — Everyone Starts Together

[S1: Interface-First Meeting — whole team, 2 hrs] --> [S2: Scope cuts + environment check] --> splits into 4 parallel lanes below

1.2 The Four Parallel Lanes (Days 1-4) — No Waiting Between Lanes

| Lane | Flow | Owner |
| --- | --- | --- |
| Lane 1 — Scoreboard | S3 (Whisper probe) -> T1 (baseline harness) | Ankit |
| Lane 2 — Semantic Retrieval | T2 (semantic FAISS index) | Divya + Aarth |
| Lane 3 — Entropy Gate | T3 (entropy gate, depends on T1+S3 finishing first) | Ankit + Mahi |
| Lane 4 — Entity Tagging | T4 (NER pipeline, depends on T1's test split existing) | Aarth + Divya |

All 4 lanes converge only once, at the end of Day 4:

[T1] + [T2] + [T3] + [T4] --> [T5: FIRST INTEGRATION CHECKPOINT — stub-wired full pipeline shape, whole team, Day 4]

HANDOFF RULE: T5 cannot start until ALL FOUR lanes report a working stub — this is the one hard wait point in the first half of the build.

1.3 Days 4-7 — Second Parallel Phase

After T5 passes, the team splits again into 3 lanes:

| Lane | Flow | Owner |
| --- | --- | --- |
| Build Lane | T7 (real correction step: few-shot Qwen2.5 wiring) | Ankit + Mahi |
| Retrieval Lane | T6 (phonetic FAISS from REAL AfriSpeech audio, RRF fusion with T2's semantic index) | Divya + Aarth |
| Data Lane | T8 (category thresholds, drafted from T1's error patterns — runs anytime after T4, no blocking) | Aarth + Divya |

[T6] + [T7] + [T8] --> [T9: SECOND INTEGRATION CHECKPOINT — full pipeline, first real ablation number, whole team, Day 7]

HANDOFF RULE: T7 (correction) needs T6's fused retrieval output as its input candidates — this is the second hard wait point.

1.4 Days 8-12 — Third Parallel Phase (Widest Parallelism, Least Waiting)

| Lane | Flow | Owner |
| --- | --- | --- |
| Safety Lane | T10 (UNSURE fallback wired into correction step) | Ankit + Mahi |
| Tuning Lane | T11 (threshold tuning + error analysis, runs parallel to T10, no dependency between them) | Aarth + Divya |
| Infra Lane | T12 (latency pass on retrieval — runs parallel to everything, only needs T6 already done) | Divya + Aarth |
| Stretch Lane (conditional) | T13 (QLoRA upgrade — ONLY if capacity allows, does not block anything else if skipped) | Ankit + Mahi |
| India Lane | T14 (frozen pipeline run on EKA + Svarah — runs fully parallel, only needs T9's frozen pipeline) | Divya + Aarth |

All lanes converge once more: [T10]+[T11]+[T12]+[T14] --> [T15: THIRD INTEGRATION CHECKPOINT, Day 12]

This is the widest parallel stretch in the whole build — 4-5 lanes running with zero cross-dependency, exactly the efficiency you asked for.

1.5 Days 13-14 — Convergence to Final Deliverable

[T15] --> [T16: Freeze ablation table + numeric corrections, Aarth+Ankit] --> [T17: Report + visualizations + demo prep, whole team] --> [T18: Final check + demo rehearsal, July 31]

──────────────────────────────────────────────────────────────────────

The visual flowchart below mirrors the text-based dependency map in Sections 1.1-1.5 exactly — use whichever is easier to present.

──────────────────────────────────────────────────────────────────────

2. Actual Calendar Mapping — July 20 to July 31, 2026

The source report's 'Day 1-14' plan is mapped onto real dates below so there is zero ambiguity about what happens when.

| Date | Day # | Milestone | Owners Active |
| --- | --- | --- | --- |
| Jul 20 (Mon) | Day 1 | S1 Interface meeting, S2 scope lock, S3 Whisper probe, T1 starts | Whole team |
| Jul 21 (Tue) | Day 2 | T1 continues, T2 continues, T3 starts, T4 starts | All 4 in parallel |
| Jul 22 (Wed) | Day 3 | T2 continues, T3 continues, T4 continues | Divya/Aarth on T2, Ankit/Mahi on T3, Aarth/Divya on T4 |
| Jul 23 (Thu) | Day 4 | T3, T4 finish -> T5 First Integration Checkpoint | Whole team, end of day |
| Jul 24 (Fri) | Day 5 | T6 starts, T7 starts | Divya/Aarth on T6, Ankit/Mahi on T7 |
| Jul 25 (Sat) | Day 6 | T6 continues, T7 continues, T8 starts | Aarth/Divya on T8 in parallel |
| Jul 26 (Sun) | Day 7 | T6, T7, T8 finish -> T9 Second Integration Checkpoint (first ablation number) | Whole team, end of day |
| Jul 27 (Mon) | Day 8 | T10 starts, T11 starts, T12 starts | Ankit/Mahi on T10, Aarth/Divya on T11, Divya/Aarth on T12 |
| Jul 28 (Tue) | Day 9 | T10, T11, T12 continue; T13 (conditional) and T14 start | Widest parallel stretch |
| Jul 29 (Wed) | Day 10 | T10, T11 finish; T12, T13, T14 continue | Widest parallel stretch |
| Jul 30 (Thu) | Day 11-12 | T12, T13, T14 finish -> T15 Third Integration Checkpoint | Whole team, end of day 12 |
| Jul 31 (Fri) | Day 13-14 (compressed) | T16 ablation table freeze, T17 report+demo prep, T18 final check and rehearsal | Whole team — DEADLINE DAY |

Note: the source report's Week 3 (Days 15-21) is explicitly framed as optional buffer/polish, not required for a complete result — your deadline of July 31 lands exactly at the end of the source plan's Day 14 core deliverable, which the report itself calls. T16-T18 are the tasks to protect first.

──────────────────────────────────────────────────────────────────────

3. Locked Scope Cuts — Decided Now, Not Discovered Mid-Sprint

These are the exact, verified scope cuts from the source report's Section 5.5, in priority order. Cutting in this order is what makes 12 days achievable at all.

| Cut | What Changes | Why This Is The Right Cut | When To Revisit |
| --- | --- | --- | --- |
| Correction LLM: QLoRA fine-tune -> few-shot prompting first | Qwen2.5-7B-Instruct (primary) or Llama-3.1 (if access clears) used via few-shot prompting against retrieved candidates, NOT fine-tuned | QLoRA data prep + training + eval + debugging costs 3-5 days on its own. Few-shot prompting against the same retrieval candidates gets a real, measurable result in under a day | Only attempt QLoRA (T13) in the second week if compute is free AND the few-shot result from Day 7 is promising enough to be worth strengthening |
| Phonetic index: skip TTS synthesis, reuse existing audio | Mine real drug-name pronunciations directly from AfriSpeech-200's own clinical clips instead of generating synthetic TTS audio | Synthesizing a drug-name TTS corpus is a multi-day side project. AfriSpeech-200 already contains real drug-name pronunciations — cuts an entire workstream without weakening the dual-retrieval claim | Not revisited — this is a permanent, better method, not a temporary shortcut |
| Evaluation datasets: AfriSpeech first, India datasets as inference-only | EKA + Svarah run through the FROZEN pipeline with zero pipeline modification, pure inference scoring | The pipeline should run unmodified on India datasets — no pipeline changes required, only a scoring run, scheduled on a day compute is otherwise idle | Not revisited — this was always the plan, restated here for clarity |
| Patent/publication packaging | Produce the ablation table and written findings; explicitly treat patent-claim drafting and submission-ready paper formatting as future work, stated openly in the report | Narrow-claim patent drafting and full paper submission formatting are not achievable in 12 days alongside the technical build | After V1 is presented and the professor's feedback is incorporated |

──────────────────────────────────────────────────────────────────────

4. The Parallelization Rule — Why Four People Won't Collide

Four workstreams can run simultaneously because they touch different files and share only TWO integration points: the scoreboard (Ankit's harness) and the fused-retrieval output (Divya/Aarth's FAISS+RRF layer), which Ankit and Mahi's gating/correction code consumes. Two rules make this work in practice, both taken directly from the verified source report.

Rule 1 — Interface-First on Day 1

The whole team agrees, in writing, the exact function signatures and data schema between components before any code is written: what a retrieval-candidate object looks like, what the entropy gate returns, what the scoreboard expects as input. This single-hour meeting (S1) is what lets four people build in parallel without waiting on each other.

Rule 2 — Merge to Main At Least Once a Day, Even Incomplete

Every person pushes a mock/stub version of their component daily that returns fake-but-correctly-shaped output, so the other three are never blocked waiting for someone's real implementation. This is why T5 (Day 4) is a STUB checkpoint, not a real-output checkpoint — it confirms shape compatibility before any component is finished.

☐ Interface contract document written and agreed by all 4 before Day 1 ends

☐ Every person has pushed at least one stub/mock commit by end of Day 2

☐ AfriSpeech-200 download kicked off as a background task at the start of the S1 meeting — 20-30GB, do not wait until the meeting ends to start it

──────────────────────────────────────────────────────────────────────

5. Ankit's Full Work — Integration, Coding, Scoreboard (Reports To: No One, Coordinates With Mahi Directly)

Ankit is the integration owner by default — holding the scoreboard means every other person's branch is measured against the same numbers the moment it merges. Read Section 0 fully before this section; every task below depends on knowing what Aarth/Divya are producing and when.

S3 — Whisper output_scores Probe (Day 1)

What: a 20-line script loading whisper-medium via HuggingFace, calling .generate() with output_scores=True and return_dict_in_generate=True on one real audio clip, printing the resulting tensor shape. Why: per-token confidence is the single hardest unknown in the whole project — the entropy gate (T3) cannot exist without it. Do this in hour one, not later, so any blocker is known immediately. How: transformers' WhisperForConditionalGeneration. Fallback: if faster-whisper is used elsewhere for speed, confirm explicitly whether its exposed log-probabilities are sufficient for Tsallis entropy before relying on it for this step specifically — if not, use the HuggingFace implementation here even if faster-whisper is used elsewhere.

☐ Script runs, tensor shape printed and confirmed sensible (a probability distribution per generated token)

T1 — Baseline Harness (Day 1-2)

What: Whisper-medium zero-shot inference + WER/M-WER/per-category Recall scoring on AfriSpeech-200's clinical test split, using jiwer. Why: nothing else in the project can be measured without this scoreboard existing first. How: jiwer for WER; M-WER is WER computed only on entity-tagged words (needs T4's NER output eventually, but a first pass can run on raw WER alone). Expect: numbers near AfriSpeech-200's published pretrained-Whisper range.

☐ Baseline WER/M-WER computed, saved, and posted to the team channel per T1's role as the running scoreboard

☐ Whisper call includes word_timestamps=True from the start — Divya needs these on Day 4 to extract drug-name audio segments for T6

T3 — Entropy Gate (Day 2-4, With Mahi)

What: implement Tsallis entropy over the confirmed token distributions from S3, output a boolean uncertainty flag per token, unit-tested in isolation from retrieval. Why: this is what makes retrieval selective instead of always-on — the project's single most novel claim (RQ1/RQ4). How: implement directly from the Tsallis formula (alpha=1/3), pure numpy. Fallback: simple max-probability thresholding if tuning proves difficult in the time box.

☐ Entropy gate implemented, unit-tested on synthetic examples, flagging rate sanity-checked (not 0%, not 100%)

T7 — Real Correction Step (Day 5-7, With Mahi)

What: wire few-shot prompting (Qwen2.5-7B-Instruct as PRIMARY, Llama-3.1 as optional upgrade only if gated access clears early) against T6's fused retrieval candidates — explicitly NO fine-tuning at this stage per the locked scope cut in Section 3. Why: proves the correction concept moves the needle before investing in QLoRA. How: standard few-shot prompt template, no training loop. Fallback: if Llama access hasn't cleared, this was never blocking — Qwen2.5 is the primary, not a backup.

☐ Correction step produces sensible outputs on 10 hand-written test cases

T10 — UNSURE Fallback (Day 8-10, With Mahi)

What: add a three-way CORRECT/WRONG/UNSURE classification to the correction step; on UNSURE, pass through Whisper's original token unchanged rather than guessing. Why: this is the safety-critical differentiator — a system that never hallucinates a correction it isn't confident about. How: prompt-based three-way classification first; structured output via outlines if time allows.

☐ UNSURE fallback tested on ambiguous cases, confirmed it passes through the original token rather than guessing

T13 — Optional QLoRA Upgrade (Day 9-12, Conditional, With Mahi)

What: ONLY attempted if Day 7's few-shot numbers are promising AND compute is genuinely free. Why: this is the explicitly optional stretch task per 3 — skipping it costs nothing structurally. Decision must be made and documented either way.

☐ Go/no-go decision on QLoRA made and documented by Day 9, not left ambiguous

T16 — Ablation Table Freeze (Day 13, With Aarth)

What: lock the final ablation table (baseline -> naive correction -> dual retrieval -> entropy-gated -> thresholded -> UNSURE) and apply the two mandatory numeric corrections from Section 7. Why: this table is the report's core results section — nothing changes after this point.

☐ Ablation table locked, all 6 rows populated with real measured numbers, no placeholder values

──────────────────────────────────────────────────────────────────────

6. Mahi's Full Work — Testing, Verification, Presenting Face (Coordinates With Ankit Directly)

Mahi is Ankit's full partner on every build task above — the coordination goal is maximum shared work between you two, so every task Ankit owns, Mahi is present for. Mahi's distinct additional ownership is testing and verification at each checkpoint, plus final demo presentation.

Testing Responsibility At Every Checkpoint

What: write and run the Definition-of-Done unit tests for every module before it's considered complete — a layer isn't done until it has a unit test on synthetic examples AND an entry in the ablation table. Why: this is what lets the team catch a broken module immediately instead of discovering it at T15's final checkpoint. How: pytest, simple hand-written test cases per module (5-10 known input/output pairs per module).

☐ T3 (entropy gate) has a passing unit test before T5

☐ T7 (correction step) has a passing unit test before T9

☐ T10 (UNSURE fallback) has a passing unit test before T15

Checkpoint Verification (Real Output, Not Assumption)

At each of the three integration checkpoints (T5, T9, T15), Mahi runs the full pipeline against 3-5 known-answer test utterances and manually confirms the output makes sense — not just that it ran without crashing. Why: an error-free run is not the same as a correct result. This is the check that prevents a hidden bug from silently corrupting the final ablation numbers.

☐ T5 checkpoint verified against real output by Mahi, independent of Ankit's own check

☐ T9 checkpoint verified against real output by Mahi, independent of Ankit's own check

☐ T15 checkpoint verified against real output by Mahi, independent of Ankit's own check

Demo Build and Presentation (T17-T18)

What: wrap the frozen pipeline in a simple Gradio interface, test it end-to-end, and rehearse presenting it — Mahi is the face of the presentation, with full hands-on familiarity from co-building every module throughout. Why: presenting something you helped build directly is more convincing than presenting something explained to you afterward. How: gr.Interface() wraps the pipeline function directly.

☐ Demo runs locally, tested by someone other than the builder

☐ Demo rehearsed with the exact utterances planned for the presentation

──────────────────────────────────────────────────────────────────────

7. Aarth's Full Work — Data Lead, Reviews Divya, Reports to Ankit

Aarth leads the data/domain workstream and consolidates Divya's heavier preprocessing output before it reaches Ankit — matching your exact reporting chain (Divya -> Aarth -> Ankit).

T2 — Semantic FAISS Index Validation (Day 1-3)

What: Divya builds the ClinicalBERT embeddings + FAISS index over RxNorm/UMLS concepts; Aarth validates by querying with 5 known drug names and confirming correct matches in top-5. Why: catches a broken index before it's relied on downstream. How: faiss.read_index() + manual spot-check queries.

☐ Semantic index validated by Aarth independently of Divya's own build check

T4 — NER Entity Tagging (Day 2-4, Leads)

What: run BioBERT/ClinicalBERT NER over the AfriSpeech clinical test set to produce MED/COND/ANA/TTP/PHI reference spans — this is what the scoreboard needs to compute M-WER (not just raw WER). Why: without tagged entity spans, M-WER cannot be computed at all, only generic WER. How: pull the pretrained BC5CDR-tuned BioBERT checkpoint from HF Hub.

☐ NER output produces tagged spans for all 5 entity categories on at least 90% of the test set

T6 — Phonetic FAISS Validation (Day 4-6)

What: Divya mines real drug-name pronunciations from AfriSpeech-200's own clinical audio (the corrected, faster method — no synthetic TTS); Aarth validates by querying with a known misheard variant and confirming the correct name appears in top-5. Why: this is the corrected approach from Section 3 — validating it early confirms the scope cut actually worked.

☐ Phonetic index validated with at least one real known phonetic-confusion example

T8, T11 — Category Thresholds & Error Analysis (Day 6-10, Leads)

What: draft category-specific thresholds (lower for MED, higher for ANA) from T1's baseline error patterns, then tune against the Week 1 ablation numbers and pull qualitative error examples for the report. Why: per-category tuning is more clinically meaningful than one global threshold, and real examples are what reviewers/professors weight most heavily.

☐ Thresholds drafted and documented with the specific error patterns that justified each value

☐ 10-15 concrete error examples (correct/wrong/UNSURE cases) pulled for the report's qualitative section

T14 — India Evaluation Sweep Consolidation (Day 9-12)

What: consolidate Divya's frozen-pipeline runs over EKA + Svarah into a single India-context results table, reported separately from the main AfriSpeech ablation table, exactly as the source plan specifies. Why: this is pure inference scoring on an already-frozen pipeline — no retraining needed, cheap to run late.

☐ India-context table complete with both EKA and Svarah results, clearly labeled as inference-only

T16 — Ablation Table Freeze (Day 13, With Ankit)

What: apply the two mandatory numeric corrections (Section 7) to the frozen ablation table before it's locked. Why: these figures are cited elsewhere in your existing documents and must match exactly, or an evaluator who knows the source papers will catch the discrepancy.

☐ Both numeric corrections applied and cross-checked against the original source figures

──────────────────────────────────────────────────────────────────────

8. Divya's Full Work — Preprocessing, Reports to Aarth

Divya carries the data-processing in the project by design  and every task below is against what the source report verified as achievable in 12 days.

T2 — Semantic FAISS Index Build (Day 1-3)

What: embed the cleaned RxNorm/UMLS concept list with ClinicalBERT, build a FAISS index (flat or IVF depending on size) over the embeddings, tested in isolation first. Why: the 'meaning-based' half of dual retrieval. How: emilyalsentzer/Bio_ClinicalBERT from HF Hub, faiss.IndexFlatL2. Run on Kaggle for the free weekly GPU quota.

☐ ClinicalBERT embeddings generated for the full cleaned concept list

☐ FAISS semantic index built and saved, spot-checked on 5 known drug names

T6 — Phonetic Retrieval, Corrected Method (Day 4-6)

What: mine REAL drug-name pronunciations directly from AfriSpeech-200's own clinical audio clips — this REPLACES the original TTS-synthesis plan entirely, per the verified scope cut in Section 3. Extract HuBERT embeddings from these real clips, build the phonetic FAISS index, RRF-fuse with the semantic index. Why: this cuts an entire multi-day side project (TTS generation) without weakening the dual-retrieval claim, since two independent retrieval channels still exist. How: identify AfriSpeech-200 clips containing drug-name mentions (cross-reference with T4's NER tags), extract HuBERT layer-9 embeddings directly from those real clips.

☐ HuBERT model downloaded before Day 4 — use facebook/hubert-base-ls960 from HuggingFace Hub (~380MB), layer-9 hidden states for phonetic embeddings — do not wait until Day 4 to discover this

☐ Real drug-name audio segments identified from AfriSpeech-200 using T4's entity tags

☐ HuBERT embeddings extracted from real (not synthetic) clips

☐ Phonetic FAISS index built, RRF fusion with semantic index implemented and tested

T12 — Latency Pass (Day 8-11)

What: batch FAISS queries and cache embeddings so the gating latency claim (RQ4) holds up under real measurement, not just theoretical estimate. Why: an unmeasured latency claim is not a defensible claim.

☐ Batch querying implemented, embedding cache in place, latency measured and logged

T14 — India Evaluation Sweep, Build (Day 9-12)

What: run the frozen Week 1 pipeline over EKA + Svarah — pure inference, zero retraining, zero pipeline modification. Why: the pipeline should run unmodified on India datasets per the source report's explicit instruction — schedule this on a day compute is otherwise idle.

☐ Frozen pipeline run completed on both EKA and Svarah without any pipeline changes

Support Role — T4, T8, T11, T16

Divya supports Aarth's-led tasks (NER tagging, threshold drafting, error analysis, ablation freeze) wherever preprocessing overlap exists, keeping the reporting flow (Divya -> Aarth) clean without duplicating ownership.

☐ All support handoffs to Aarth logged before each respective deadline

──────────────────────────────────────────────────────────────────────

9. Testing & Verification Framework — Output-Based At Every Checkpoint

Every check below verifies against actual produced output, never just 'the code ran without an error.'

| Checkpoint | What Gets Verified | How | Owner |
| --- | --- | --- | --- |
| T5 (Day 4) | Pipeline SHAPE works end-to-end — stub components return correctly-shaped fake output | Run the full stub-wired pipeline on 1 test utterance, confirm no shape mismatches at any handoff point | Mahi verifies, whole team confirms |
| T9 (Day 7) | First real ablation number — dual retrieval + few-shot correction actually improves M-WER over baseline | Run on the full AfriSpeech test split, compare against T1's baseline number directly | Ankit computes, Mahi independently verifies |
| T15 (Day 12) | Full pipeline with UNSURE fallback + tuned thresholds, scored on AfriSpeech AND India datasets | Run on both, confirm UNSURE rate is non-zero but not excessive, confirm India results are plausible relative to AfriSpeech | Whole team, Mahi leads output verification |
| T16 (Day 13) | Every number in the frozen ablation table traces to an actual saved results file, not a remembered/estimated value | Cross-check every table cell against its source CSV before locking | Aarth + Ankit |

9.1 Per-Module Unit Tests (Mahi-Owned, Before Each Checkpoint)

| Module | Test Method | Pass Criteria |
| --- | --- | --- |
| Entropy gate (T3) | 5 sentences with a known hard word | Gate flags that specific word, not a random one |
| NER (T4) | 10 known drug names | At least 8/10 correctly tagged |
| Semantic FAISS (T2) | 5 known drug names | Correct name/synonym in top-5 |
| Phonetic FAISS (T6) | 1 known real phonetic-confusion example from AfriSpeech | Correct name in top-5 |
| Correction step (T7) | 10 hand-written CORRECT/WRONG/UNSURE cases | At least 8/10 match expected label |

9.2 Final Whole-System Check (Before Calling V1 Done, July 31)

☐ Every checkbox in Sections 5-8 is checked

☐ T16's final ablation table shows measurable, non-zero improvement at each stage (baseline -> naive -> dual -> entropy -> thresholded -> UNSURE)

☐ India-context table (T14) reported separately, clearly labeled as inference-only, not hidden or blended into the main table

☐ Demo tested end-to-end by someone other than its builder

☐ All 4 people confirm their own section of the report accurately reflects their actual work

──────────────────────────────────────────────────────────────────────

10. Numeric Corrections — Apply These Exact Figures, Nowhere Else

These 2 corrections are verified directly from your own Checks document and must be applied consistently throughout the final report, not left as the original incorrect figures.

| Figure | Incorrect Version (Do Not Use) | Corrected Version (Use This) | Source |
| --- | --- | --- | --- |
| MedHallu UNSURE precision gain | 10-15% | Up to 38% | Verified against the MedHallu paper/GitHub directly |
| Tsallis entropy multiplier | A flat 4x | A 1.5-4x range | Verified against Laptev & Ginsburg's original formulation |

Additionally: pull the exact JMIR CER figure from its source table before citing it anywhere in the final report — do not restate it from memory.

──────────────────────────────────────────────────────────────────────

11. Claims Table — What V1 Can Honestly State, By Person and Total

Populate the measured-result column only once actual numbers exist from T16's frozen ablation table — do not fill in estimated numbers ahead of time.

| Owner | Claim | Status By July 31 |
| --- | --- | --- |
| Ankit | Built and validated the confidence-scoreboard (WER/M-WER/Recall) that every other result in this project is measured against | [ ] Complete — number: ____ |
| Ankit + Mahi | Implemented Tsallis entropy-gated selective retrieval, replacing always-on retrieval, with a measured latency comparison | [ ] Complete — improvement: ____ |
| Ankit + Mahi | Implemented the three-way CORRECT/WRONG/UNSURE safety gate — on UNSURE, the system passes through Whisper's original token rather than guessing | [ ] Complete — UNSURE rate: ____ |
| Divya (build), Aarth (validate) | Built a working dual-retrieval system (semantic + phonetic FAISS, RRF-fused) using REAL AfriSpeech audio for phonetic matching, not synthetic TTS | [ ] Complete — top-5 accuracy: ____ |
| Aarth (lead), Divya (support) | Tagged MED/COND/ANA/TTP/PHI entity spans across the AfriSpeech test set, enabling true M-WER (not just generic WER) measurement | [ ] Complete — coverage: ____% |
| Aarth + Divya | Ran the frozen pipeline on India-context data (EKA + Svarah) as a separate, honestly-labeled inference-only evaluation | [ ] Complete — results table: ____ |
| Whole team | Produced a complete ablation table (baseline -> naive correction -> dual retrieval -> entropy-gated -> thresholded -> UNSURE) with every number traceable to a saved results file | [ ] Complete |
| Mahi | Built and rehearsed a working live demo, tested end-to-end by someone other than the builder | [ ] Complete |
| TOTAL PROJECT CLAIM | A working, confidence-gated, dual-retrieval clinical ASR correction pipeline with a measured, honest ablation table across 1 primary + 2 India-context datasets, delivered by July 31, 2026 | [ ] V1 COMPLETE |

──────────────────────────────────────────────────────────────────────

12. What Is Explicitly NOT Done By July 31 — Stated Honestly, Not Hidden

Per the source report's own explicit instruction, treat these as stated future work in the report itself, not silently-dropped scope.

QLoRA fine-tuning of the correction model — attempted only as a conditional stretch task (T13); few-shot prompting is the shipped V1 baseline

Fully-tuned per-category thresholds — a first-pass tuning happens (T11), full convergence is future work

Narrow-claim patent drafting and submission-ready paper formatting — explicit future work, not part of V1's Definition of Done

CoSHE-Eval dataset — not in the 12-day scope; EKA + Svarah cover the India-context claim sufficiently for V1

13. If Behind Schedule — What To Protect First

If any single checkpoint slips, protect these in this exact order — matches the source report's own minimum-viable-scope logic.

| Priority | Protect This | Because |
| --- | --- | --- |
| 1st priority | T1 (baseline) + T9 (first real ablation number) | This alone answers whether dual retrieval improves M-WER — the project's core hypothesis |
| 2nd priority | T10 (UNSURE fallback) | The clinical-safety differentiator — the single most defensible claim if time is short |
| 3rd priority | T14 (India sweep) | Cheap to run late since it's pure inference — cut last, not first |
| Cut first if truly out of time | T13 (QLoRA) | Already explicitly optional — costs nothing structurally to skip |

──────────────────────────────────────────────────────────────────────

CARE-ASR Final Execution Plan